## Release_Plan
Greensheets Redesign Release Plan
| Start | End | Status/Notes
QA | 2017-07-24 | 2017-10-16 |  | Greensheets Redesign Sprint SDLC Timeline
Sprint 1 - Walkthroughs/Test Case Planning | 2017-05-31 | 2017-07-03 | Complete!
Sprint 1- Functional Testing | 2017-07-24 | 2017-08-31 | Pending Release of Functionalities | Greensheets Redesign Sprint SDLC Timeline
Sprint 1 - Section 508 Testing | 2017-08-01 | 2017-08-04 |  | 2017-07-21 | First Functionalities available for QA
Sprint 1 - Regression Testing | 2017-08-21 | 2017-09-01 |  | 2017-07-31 | Development Cycle Expected to be Completed
Sprint 2 - UAT Testing | 2017-09-01 | 2017-09-30 | Estimated Dates | 2017-07-28 | Formal kickoff date for QA Testing
Sprint 2 - Post-UAT Feedback QA Testing | 2017-09-18 | 2017-10-13 | Plan on simultaneous testing with UAT | 2017-09-01 | Completion Date for QA Testing prior to UAT
Sprint 2 - Final Round of Regression Testing | 2017-10-02 | 2017-10-13 |  | 2017-09-01 | UAT Testing Commenced Date (Estimate)
|  |  |  | 2017-09-30 | UAT Testing Completed
|  |  |  | 2017-09-18 | QA Testing Post UAT Feedback (Hot-Fixes, Changes, Missed Requirements)
|  |  |  | 2017-10-16 | Hard Date for Greensheets Redesign Testing Completion
| Start | End
Sprint 1 | 2017-03-18 | 2017-08-25
Requirements and Walkthroughs | 2017-05-26 | 2017-06-30
Development | 2017-06-01 | 2017-07-31
Testing (Functional, 508 and Regression) | 2017-07-28 | 2017-08-31
Stage Preparation and Testing | 2017-08-21 | 2017-09-01
Sprint 2
UAT Testing | 2017-09-01 | 2017-09-29
UAT Fixes/Feedback for QA and Regression Testing | 2017-09-15 | 2017-10-06
Stage Preparation and Testing | 2017-10-06 | 2017-10-13
Hard Cutoff Date for Dev/Testing Completion (Current) |  | 2017-10-16