## Slide 1: GreenSheets Re-design Project OGA Meeting
Presented on: 28-June-2016

## Slide 2: Introductions
Key Business Stakeholders:
  Business Owner(s): Crystal Wolfrey, (OGA Chief)
  Business Stakeholder: Stacey Kocher
  Subject Matter Expert: Eugenia Chester
    CBIIT Team Members
  Nelya Gunina, Federal Project Manager
  Jennifer Kwok, Federal Project Manager
  Lawrence Brem, Technical Project Manager
  Gerald Momplaisir, Technical Lead
  Yakov Polonsky, Architect
  Subashini Varadarajan, Requirements Analyst
  Gabriella Tulchinskaya, Requirements Analyst
  David Chang, Database Developer

## Slide 3: Meeting purpose
  Communicate to OGA that CBIIT already started working on the project
  Provide overview of the project scope
  Describe project plan and phased approach
  Discuss October 15th deadline and other dependencies
  Communicate that CBIIT will be reaching out to various SME(s)
  Discuss next steps

## Slide 4: Work already started
CBIIT already completed analysis phase:
  Analysis of production issues that should be addressed by re-design
  Existing technology stack that should be upgraded
  Analysis of additional business needs (previously collected and new)
  Created the list of recommendations for re-design

## Slide 5: Project scope overview
Fix recurring production issues
    Greensheets Submission (Major reoccurring issue (PD Greensheet)
    Greensheets Timeout (Major reoccurring issue)
    Duplicate greensheets (only reoccurring occasionally)
    Attachments issue (new)
Accommodate additional business needs:
      Previously agreed upon:
        Provide reporting capabilities
    Ad-hoc (congressional) reports on statistics related to answers to a specific question
    User-friendly dashboard report to easily access the grants and the underlying greensheets and also to help visualize some of the key metrics. This is house-keeping” reports, for example ‘how many greensheets in Submitted status
        Enhance search capabilities
        Enhance security
        UI modernization and usability (e.g. add a link to policy for each or some questions)
        New (proposed):
        Address needs with revised awards and supplements
        Form Builder integration changes (e.g. breaking up modules into smaller parts and deploying separately, using additional capabilities of FB)
        Changes to business flow and navigation
        Compliance document retention policy

## Slide 6: 3. Project plan and phased approach
Phase | Description | Time frame
Non-UI reporting | A new approach to extracting questions from Form Builder and saving them in different tables. This approach will prepare the database to handle reporting requirements with ease. | From now to beginning of 2016 FY
Upgrade technology stack | Will enhance security | From mid-September until mid-March
UI modernization and usability, enhancing search capabilities, addressing production issues related to UI and technology upgrade | Requirements will be collected as soon as possible; implementation depends on completion of prior phases. Examples: address needs with revised awards and supplements; add a link to policy for each or some questions. | From mid-July 2016 until end of the project
Integration with external systems | Example: Form Builder - breaking up modules into smaller parts and deploying separately, using additional capabilities of FB | From mid-July 2016 until end of the project
Provide UI reporting capabilities | This phase might be not necessary if OGA will use other tools for reporting purposes | Spring-summer 2017

## Slide 7: October 15th deadline and other dependencies
  Please confirm that future requests for ad-hoc reporting will be only for the data collected STARTING October 15, 2016 (new FY) and historical data is NOT needed for reporting (clean-start approach).
  Is there a real business need to go into production with database redesign on October 15h deadline? Or would it be acceptable just to make sure that when time for ad-hoc congressional reporting comes, the data for the whole FY2017 is available?
  Does business process allow to shut down GreenSheets system for a certain period of time (e.g. 2 weeks)?
  Requirements solicitation progress depends on stakeholders’ availability
  Need to re-design dummy grants reconciliation process in GPMATS in order to address duplicate greensheets issue. Can OGA be responsible for deletion of duplicate greensheets?
  Do we have to comply with document retention policy?

## Slide 8: CBIIT will be reaching out to SME(s)
CBIIT will be reaching out to business owners and OGA stakeholders during all remaining phases of the project
Our analysis indicated that Program staff has specific GreenSheets needs (e.g. specific search needs). We recommend brining several Program SME to provide requirements feedback for particular topics

## Slide 9: Next Steps
    CBIIT to schedule requirements elicitation sessions with Business Owner and Business Stakeholders. Sessions will start in July 2016
    OGA to identify other Subject Matter Experts (SMEs) who will be involved in the project, as needed. Next session will be dedicated to clarification of requirements for ad-hoc reporting.